## mainProcedure
Version | 0.0
DESIGNATIONS
| MC | Mission Control/Operations -> alternative OP
| GS | Ground Support
| RM | Rocket Motor -> the ones outside
| El | Electronics
| SF | Safety
T- | STATION | ACTION | Checkbox | Value | Time | Comment
| Phase | Green
T-2h | MC | Anounce countdown start
| MC | Anounce Phase Green
Electronics
| Phase | Reset the software into TEST mode and run the tests.
|  | Ground the test pin 0 (Arduino pin 23) and reset the Arduino Mega. |  | Pre procedure?
Press Arduino reset button while testpin is grounded
| El | Confirm that the Green LED is on
| Phase | Not applicable in version V1 - Verify the heating blanket can be controlled by the software.
| El | Ground the test pin 2 (Arduino pin 27)
| El | Equates to valve mosfet 2.
| Phase | Verify the full firing sequence works and timing is correct. |  |  |  |  | Order:
| El 2 | Start the software in test mode by grounding test pin 0 and pressing the reset button on the Arduino |  |  |  |  | Primary Igniter relays when GS presses button.
|  | Confirm test mode Green LED is on |  |  |  |  | Secondary igniter relay after ~1 second.
| El 2 | Enter Forced sequence by grounding test pin 5 |  |  |  |  | Oxidizer valve opens after ~2 seconds.
Confirm Red LED is on
| El 1 | confirm readiness to Measure that the igniter circuit gets a voltage (~24V). |  |  |  |  | Secondary igniter relay after ~3 seconds.
| El 2 | confirm readiness to Listen to relays and valves and make sure they are activated. |  |  |  |  | Oxidizer valve after N seconds (depends on the wanted burn length, 6-10 seconds).
| GS | GSE presses the ignition button |  |  |  |  | Primary Igniter relays after GS releases button.
| El 1 | Confirm measurement
| El 2 | Confirm audibly click
| Phase | Not applicable in version V1 - Verify valves can be controlled by the software.
| El | Test each of the valves individually and verify they can be opened.
| El | This version uses only one valve. Other mosfets can be used for buzzer and heating blanket.
| Phase | Not applicable in version V1 - Verify servos can be controlled by the software.
| El | Run the servos through a sweep sequence.
| Phase | Verify the software can be reset through the software. By grounding test pin 6
| El | Confirm with GSE that they heard the reset buzzer
| Phase | Verify Software is switched off from TEST mode.
| El | Press the button to Software is reset with a power cycle
| El | Confirm with GSE that they heard the reset buzzer
| GS | Confirm that Pressure sensor is sending data
| GS | Confirm that Thermocouple is sending data |  | Move if nessesary
| GS | Confirm that IR-sensor is sending data
| GS | Confirm that Load cell is sending data
T-30 | PHASE | Priming Rocket System
| All | Anouncement: Authorized personel is RM team with PPE
| RM | Put on PPE
| SF | Confirm test site is clear of all unauthorized personnel
| MC | Announce PHASE YELLOW
| RM | Put on ESD protection wristband.
| RM | Confirm ESD protection wristband is connected to ground.
| RM | Preassure check
| RM | Confirm N20 bottle hose connector is attached.
| RM | Start camera recording.
| RM | Grab Multimeter and verify the function with a 9V battery
| RM | Verify voltage between leads is less than 10mV
| RM | Verify voltage from each lead to ground is less than 50mV
| GS | Confirm Oxidizer Valve is closed.
| RM | Take positions for N2O bottle opening.
| RM | Stepwise open N2O bottle and check for leakage. If leakage occurs close N2O bottle immediately and switch to Abort procedure.
| RM/GS | Check & compare pressures @Bottle-Gauge and @P-Bottle. If above 70 bar switch to Abort procedure!
| RM | Move to operation center.
| PHASE | Ignition Preparations
Anounce Phase RED
Heating of bottle
T-0 | PHASE | Ignition Sequence
| Phase | Purging
T+ |  | Confirm that Oxidiser valve is closed
Confirm preassure sensor value is below TBD and stable
PPE
Anouncement:
Wait for TBD
Move to test site
Check bottle gauge
Close N2O bottle
Return to Operation Center
Venting
Confirm that the pressure is 0
Wait for TBD
PPE
Move to test site
Confirm that the bottle gauge is 0
Confirm safety
Turn of the camera
Check data
End countdown

## Countdown list
T- | STATION | Mission Control | Ground Support | Electronics | Rocket Motor | Safety | Checklist
T-2h |  | Countdown Start
Phase Green
General
|  |  | Communications | Communications
|  |  | Sensors | Sensors
|  |  | Control | Control
Area clear of unatirized personel
PPE
T-30 |  | Phase Yellow
N2O
Camera
Ignitor
Valve
Valve
N2O
Area clear of all personel
Phase Red
Ignitions sequence

## Roles
Roles |  | People | Attendance
MC | Mission Control | Lukas |  | FALSE
SF | Safety | Alexandra |  | FALSE
Electronics Team
GS | Groundsupport | Eemeli |  | FALSE
CM | Communication | Sebastian |  | FALSE
EL1 | Electronics 1 | Ivar |  | FALSE
EL2 | Electronics 2 | Johannes |  | FALSE
Engine team
Rocket Motor - RM
SUP | Supervisor | Sebbe |  | FALSE
ES1 | Engine setup 1 | Ganesh |  | FALSE
ES2 | Engine setup 2 | Rodrigo |  | FALSE

## ElectronicPreProcedures
The checking have to be done sequentially to ensure the systems works in the correct way and all steps are correctly followed.
|  |  | Select/Deselect All |  | FALSE
ID | T- | Action | Pre Procedures
|  |  |  | Checkbox | Checkbox links
|  | Phase | General
1 |  | EL1 | Mains power available at test location |  | FALSE
2 |  | EL1 | Measure PSU input for shorts |  | FALSE
3 |  | EL1 | Measure PSU output for shorts |  | FALSE
4 |  | GS | Check that umbilical is connected to controlbox |  | FALSE
5 |  | EL1 | Check that the umbilical is connected at the test bench |  | FALSE
6 |  | EL1 | Plug in the power supply to mains power. |  | FALSE
7 |  | EL1 | Plug in the Rock 4C+ power brick to mains power. |  | FALSE
|  | EL1 | Confirm that there is no smoke. |  | FALSE
|  | Phase | Measure voltages on the power board
|  | EL1 | Verify multimeter function with a 9V battery |  | FALSE
|  | EL1 | Measure 24V voltage output of the PSU |  | FALSE
|  | EL1 | Not applicable in version V1 - Expected Rock 4C+ voltage is 5.1V |  | FALSE
|  | EL1 | Not applicable in version V1 - Expected Servo voltage is 7.8V |  | FALSE
|  | EL1 | Expected Arduino voltage is 7.8V |  | FALSE
|  | EL1 | Measure Arduinos internal 5V voltage |  | FALSE
Electronics Comunications
|  | Phase | Ensure the following:
|  | EL1 | Rock 4C+ power on |  | FALSE
|  | EL1 | USB connection between Rock 4C+ and Arduino (Using a no power USB cable) |  | FALSE
|  | EL1 | Ethernet cable connection between Rock 4C+ and laptop |  | FALSE
|  | Phase | Setting up the laptop terminal
|  | CM | Start the Tilix terminal application on the laptop (windows button and then search) |  | FALSE
|  | CM | Use ctrl+alt+a to open a new terminal window inside Tilix (3 should be enough) |  | FALSE
|  | CM | Left click or use alt+[arrow key] to navigate between terminal windows |  | FALSE
|  | Phase | Data reading and backup
|  | CM | Use “ ping rock-4c-plus.local ” to ensure ethernet connection and confirm zero packet loss |  | FALSE
|  | CM | Use " ssh rock@rock-4c-plus.local ” to remote connect to Rock 4C+ |  | FALSE
|  | CM | In the ssh terminal (opened in previous step) use " sudo python3 scripts/serial_reader.py ” to start reading serial data and save it to the Rock 4C+ |  | FALSE
|  | CM | Use “ ssh rock@rock-4c-plus.local “tail -f scripts/data.csv” ¦ tee data.csv ” to get a live reading of the sensor data and write it locally to the laptop |  | FALSE
|  | CM | Use “python3 live_grapher_opt_V2.py” to start live graphing the sensor data |  | FALSE
|  | Phase | Coordinate with GSE (Control Box Operator)
|  | GS | Verify that the main power relay can be activated from the control box. |  | FALSE
|  | GS | Confirm that E-Stop button not pressed. |  | FALSE
|  | EL 1 | Measure the voltage between PSU_24V and 24V. |  | FALSE
|  | EL1 | Confirm 0 voltage |  | FALSE
|  | GS | Confirm that E-Stop button pressed. |  | FALSE
|  | EL1 | Measure the voltage between PSU_24V and 24V. |  | FALSE
|  | EL 1 | Confirm 24 V |  | FALSE
|  | Phase | Verify that the two primary ignition relays can be activated from the control box.
|  | GS | GS confirms ignition button and key are not pressed. |  | FALSE
|  | EL1 | EL 1 measures continuity between IGN_GND and PGND |  | FALSE
|  | EL1 | EL 1 confirms no continuity. |  | FALSE
|  | El1 | EL 1 measures voltage between 24V and IGNISENSE |  | FALSE
|  | EL1 | EL 1 confirms 24V voltage. |  | FALSE
|  | GS | GS confirms ignition button and key are pressed. |  | FALSE
|  | EL1 | EL 1 measures continuity between IGN_GND and PGND |  | FALSE
|  | EL1 | EL 1 confirms continuity. |  | FALSE
|  | EL1 | EL 1 measures voltage between 24V and IGNISENSE |  | FALSE
|  | EL1 | EL 1 confirms <50mV voltage. |  | FALSE
|  | Phase | Verify that the heating blanket relay can be activated from the control box.
|  | GS | GS confirms heating blanket button is not pressed. |  | FALSE
|  | EL1 | EL 1 measures voltage between 24V and HEATING |  | FALSE
|  | EL1 | EL 1 confirms 24V voltage. |  | FALSE
|  | GS | GS confirms heating blanket button is pressed. |  | FALSE
|  | EL1 | EL 1 measures voltage between 24V and HEATING |  | FALSE
|  | EL1 | EL 1 confirms <50mV voltage. |  | FALSE
|  | Phase | Verify the oxidizer valve can be activated from the control box.
|  | El1 | EL 1 confirm readiness to listen for the valve actuation. |  | FALSE
|  | GS | GS press manual valve button. |  | FALSE
|  | EL1 | EL 1 confirm the valve opens. |  | FALSE
|  | GS | GS release the manual valve button. |  | FALSE
|  | EL1 | EL 1 confirm the valve closes. |  | FALSE
Sensor
|  | Phase | Pressure sensor
|  | El2 | Ensure that the sensor is plugged in and powered. |  | FALSE
|  | EL2 | Verify with Communications that data is being received from Pressure Sensor 3 (Combustion Chamber) and that the values being received are equivalent to ambient pressure. |  | FALSE | Do this 3 times
|  | EL2 | Verify with Communications that data is being received from Pressure Sensor 2 (Post solenoid) and that the values being received are equivalent to ambient pressure. |  | FALSE
|  | EL2 | Check bottle pressure via gauge |  | FALSE
|  | EL2 | Verify with Communications that data is being received from Pressure Sensor 1 (Bottle) and that the values being received are equivalent to pressure reading from bottle gauge. |  | FALSE
|  |  | If any of the sensors are not sending data, check sensor connections and then repeat the verification procedure for that sensor. |  | FALSE
|  | Phase | Thermocouples
|  | El2 | Ensure that the sensor is plugged in and powered. |  | FALSE
|  | EL2 | Verify with Communications that data is being received from TC4 (Nozzle) and that the values being received are equivalent to ambient temperature. |  | FALSE
|  | EL2 | Spike the data from TC4 using TBD and verify with Communications that the data spiked. |  | FALSE | Do this 4 times
|  | EL2 | Verify with Communications that data is being received from TC3 (TBD) and that the values being received are equivalent to ambient temperature.
Spike the data from TC3 using TBD and verify with Communications that the spike was seen in the data being received.
|  | EL2 | Verify with Communications that data is being received from TC2 (TBD) and that the values being received are equivalent to ambient temperature.
Spike the data from TC2 using TBD and verify with Communications that the spike was seen in the data being received.
|  | EL2 | Verify with Communications that data is being received from TC1 (Heating blanket) and that the values being received are equivalent to ambient temperature.
|  | EL2 | Spike the data from TC1 using TBD and verify with Communications that the spike was seen in the data being received.
If any of the thermocouples are not sending data, check sensor connection and then repeat the verification procedure for that sensor.
|  | Phase | IR-sensor
|  | EL2 | Ensure that the sensor is plugged in correctly and that it is powered. If the sensor is powered a green LED will flash at the base of the sensor.
Verify (preferably using a thermocouple in some way) that it is providing values close to ambient temperature.
If the IR-sensor is not sending data, check connections and then repeat the verification procedure.
Spike the data using TBD and verify with Communications that the spike was seen in the data being received.
|  | Phase | Load Cell
|  | El2 | Ensure that the sensor is plugged in and powered. |  | FALSE
|  | El2 | Verify that the load cell, when no force is being applied, is only outputting the value zero. If it does not, the offset from the oxidizer piping has not been taken into account properly, or it has changed. In this case the offset can be accounted for manually with later values. |  | FALSE
|  | El2 | Apply force to the load cell and verify that this also leads to a spike in the received data.
Full sequence test
Primary Igniter relays when GS presses button.
Secondary igniter relay after ~1 second.
Oxidizer valve opens after ~2 seconds.
Secondary igniter relay after ~3 seconds.
Oxidizer valve after N seconds (depends on the wanted burn length, 6-10 seconds).
Primary Igniter relays after GS releases button.
Signature EL:
Signature MC:

## EnginePreProcedures
|  |  | Select/Deselect All |  | FALSE
ID | T- | Action | Pre Procedures
|  |  |  | Checkbox | Checkbox links
|  | RM | Move bottle from cabinet to trolley
|  | RM | Secure bottle to bottle trolley
|  | RM | Attatch piping