## mainProcedure
Version | 0.0
| DESIGNATIONS |  |  |  | Phases in bold
| MC | Mission Control/Operations -> alternative OP
| GS | Ground Support
| RM | Rocket Motor -> the ones outside
| El | Electronics
| SF | Safety
T- | STATION | ACTION | Checkbox | Value | Time | Comment
| Phase | Green
T-2h | MC | Anounce countdown start |  |  |  | Move bottle from cabinet to trolley
| MC | Anounce Phase Green |  |  |  | Secure bottle to bottle trolley
Attatch piping
| Phase | General
Mains power available at test location
Measure PSU input for shorts
Measure PSU output for shorts
Plug in the power supply to mains power.
|  | Plug in the Rock 4C+ power brick to mains power. |  | New
Check that umbilical is connected to controlbox
Look for smoke.
| Sub-Phase | Measure voltages on the power board
|  | Verify multimeter function with a 9V battery |  |  |  | At top
|  | Measure 24V voltage output of the PSU |  | 7.77
Not applicable in version V1 - Expected Rock 4C+ voltage is 5.1V
Not applicable in version V1 - Expected Servo voltage is 7.8V
|  | Expected Arduino voltage is 7.8V |  | 23.9
Measure Arduinos internal 5V voltage
| Phase | Electronics Comunications
| Sub-Phase | Ensure the following:
| El | Rock 4C+ power on
| El | USB connection between Rock 4C+ and Arduino (Using a no power USB cable)
| El | Ethernet cable connection between Rock 4C+ and laptop
| Sub-Phase | Setting up the laptop terminal
| El | Start the Tilix terminal application on the laptop (windows button and then search)
| El | Use ctrl+alt+a to open a new terminal window inside Tilix (3 should be enough)
| El | Left click or use alt+[arrow key] to navigate between terminal windows
| Sub-Phase | Data reading and backup
| El | Use “ ping rock-4c-plus.local ” to ensure ethernet connection and confirm zero packet loss
| El | Use " ssh rock@rock-4c-plus.local ” to remote connect to Rock 4C+
| El | In the ssh terminal (opened in previous step) use " sudo python3 scripts/serial_reader.py ” to start reading serial data and save it to the Rock 4C+
| El | Use “ ssh rock@rock-4c-plus.local “tail -f scripts/data.csv” ¦ tee data.csv ” to get a live reading of the sensor data and write it locally to the laptop
| El | Use “python3 live_grapher_opt_V2.py” to start live graphing the sensor data
add calibration
|  | Start countdown |  | New
| Phase | Electronics Sensor
| Sub-Phase | Preassure sensor
| El | Ensure that the sensors are correctly plugged in and that they are powered. |  | check for every sensor |  | 3 sensors
| El | Confirm whether or not the sensor has started generating data going to the laptop. |  | pre solinoid post solinoid combustion chamber
| El | Determine whether or not the data that is being received is close to what is expected, i.e., ambient pressure everywhere except for in the oxidizer tank.
| Sub-Phase | Thermocouples |  |  |  | 4 sensors
| El | Ensure that the sensors are plugged in correctly. |  | pre countdown
| El | Verify that the data being received by the laptop is equivalent to ambient temperature. If possible, spike the data using the body temperature from a hand or finger (or something else, TBD) to ensure that the sensor reacts to changing temperatures.
| Sub-Phase | IR-sensor
| El | Ensure that the sensor is plugged in correctly and that it is powered. If the sensor is powered a green LED will flash at its “base”.
| El | Verify (preferably using a thermocouple in some way) that it is providing values close to ambient temperature. This value will not be exactly right, since the emissivity value in the sensor settings will be set for measuring the engine exhaust plume. If possible, spike the data to ensure that the sensor reacts to changing temperatures.
| Sub-Phase | Loadcell
| El | Ensure that the sensor is plugged in and powered.
| El | Verify that the load cell, when no force is being applied, is only outputting the value zero. If it does not, the offset from the oxidizer piping has not been taken into account properly, or it has changed. In this case the offset can be accounted for manually with later values.
| El | Apply force to the load cell and verify that this also leads to a spike in the received data.
| Phase | Electronics Control
| Phase | 1. Reset the software into TEST mode and run the tests.
| Sub-Phase | Ground the test pin 0 (Arduino pin 23) and reset the Arduino Mega.
|  | Press Arduino reset button while testpin is grounded |  | New
| El | Confirm that the Green LED is on
Sub-Phase
El
El
| Sub-Phase | Not applicable in version V1 - Verify the heating blanket can be controlled by the software.
| El | Ground the test pin 2 (Arduino pin 27)
| El | Equates to valve mosfet 2.
| Sub-Phase | Verify the full firing sequence works and timing is correct. |  |  |  |  | Order:
| El 2 | Start the software in test mode by grounding test pin 0 and pressing the reset button on the Arduino |  |  |  |  | Primary Igniter relays when GS presses button.
|  | Confirm test mode Green LED is on |  |  |  |  | Secondary igniter relay after ~1 second.
| El 2 | Enter Forced sequence by grounding test pin 5 |  |  |  |  | Oxidizer valve opens after ~2 seconds.
Confirm Red LED is on
| El 1 | confirm readiness to Measure that the igniter circuit gets a voltage (~24V). |  |  |  |  | Secondary igniter relay after ~3 seconds.
| El 2 | confirm readiness to Listen to relays and valves and make sure they are activated. |  |  |  |  | Oxidizer valve after N seconds (depends on the wanted burn length, 6-10 seconds).
| GS | GSE presses the ignition button |  |  |  |  | Primary Igniter relays after GS releases button.
| El 1 | Confirm measurement
| El 2 | Confirm audibly click
| Sub-Phase | Not applicable in version V1 - Verify valves can be controlled by the software.
| El | Test each of the valves individually and verify they can be opened.
| El | This version uses only one valve. Other mosfets can be used for buzzer and heating blanket.
| Sub-Phase | Not applicable in version V1 - Verify servos can be controlled by the software.
| El | Run the servos through a sweep sequence.
| Sub-Phase | Verify the software can be reset through the software. By grounding test pin 6
El
| El | Confirm with GSE that they heard the reset buzzer
| Phase | 2.Verify Software is switched off from TEST mode.
| El | Press the button to Software is reset with a power cycle
| El | Confirm with GSE that they heard the reset buzzer
| Phase | 3. Coordinate with GSE (Control Box Operator) |  | Pre countdown
| GS | Verify that the main power relay can be activated from the control box. |  | Pre countdown
| GS | Confirm that E-Stop button not pressed. |  | Pre countdown
| El 1 | Measure the voltage between PSU_24V and 24V. |  | Pre countdown
| El1 | Confirm 0 voltage |  | Pre countdown
| GS | Confirm that E-Stop button pressed. |  | Pre countdown
| El1 | Measure the voltage between PSU_24V and 24V. |  | Pre countdown
| El 1 | Confirm 24 V |  | Pre countdown
Pre countdown
| Sub-Phase | Verify that the two primary ignition relays can be activated from the control box. |  | Pre countdown
| El | Both with ignition button and key not activated and activated. |  | Pre countdown
| El | Measure continuity between IGN_GND and PGND |  | Pre countdown
| El | Measure continuity between 24V and IGNISENSE |  | Pre countdown
Pre countdown
| Sub-Phase | Verify that the heating blanket relay can be activated from the control box. |  | Pre countdown
| El | Both with heating blanket button activated and not activated. |  | Pre countdown
| El | Measure continuity between 24V and HEATING |  | Pre countdown
T-30 | PHASE | Priming Rocket System
| All | Anouncement: Authorized personel is RM team with PPE
| RM | Put on PPE
| SF | Confirm test site is clear of all unauthorized personnel
| MC | Announce PHASE YELLOW
| RM |  |  | New
RM
Put on ESD protection wristband.
Confirm ESD protection wristband is connected to ground.
| RM | Preassure check
| RM | Confirm N20 bottle hose connector is attached.
RM
| RM | Start camera recording.
RM
| RM | Grab Multimeter and verify the function with a 9V battery
| RM | Verify voltage between leads is less than 10mV
| RM | Verify voltage from each lead to ground is less than 50mV
RM
RM
RM
RM
| RM | Connect Igniter cables to ignition circuit.
| RM | Confirm Manual vent valve is closed.
| GS | Confirm Oxidizer Valve is closed.
GS
| RM | Take positions for N2O bottle opening.
RM
| RM | Stepwise open N2O bottle and check for leakage. If leakage occurs close N2O bottle immediately and switch to Abort procedure.
| RM/GS | Check & compare pressures @Bottle-Gauge and @P-Bottle. If above 70 bar switch to Abort procedure!
| RM | Move to operation center.
| PHASE | Ignition Preparations
Anounce Phase RED
Heating of bottle
T-0 | PHASE | Ignition Sequence
| Phase | Purging
T+ |  | Confirm that Oxidiser valve is closed
Confirm preassure sensor value is below TBD and stable
PPE
Anouncement:
Wait for TBD
Move to test site
Check bottle gauge
Close N2O bottle
Return to Operation Center
Venting
Confirm that the pressure is 0
Wait for TBD
PPE
Move to test site
Confirm that the bottle gauge is 0
Confirm safety
Turn of the camera
Check data
End countdown
| Phase | VERY LATE INTO THE PROCEDURES: Measure igniter circuit voltage before attaching the igniter.
Before each measurement, measure a 9V battery to verify the function of the multimeter.
Verify voltage between leads is less than TBD
Verify voltage from each lead to ground is less than TBD

## Countdown list
T- | STATION | Mission Control | Ground Support | Electronics | Rocket Motor | Safety | Checklist
T-2h |  | Countdown Start
Phase Green
General
|  |  | Communications | Communications
|  |  | Sensors | Sensors
|  |  | Control | Control
Area clear of unatirized personel
PPE
T-30 |  | Phase Yellow
N2O
Camera
Ignitor
Valve
Valve
N2O
Area clear of all personel
Phase Red
Ignitions sequence

## Roles
|  | Person 1 | Person 2
MC | Mission Control | Lukas | Alexandra
GS | Groundsupport | Eemeli
CM | Communication | Sebastian
EL | Electronics | Ivar | Johannes
| Rocket Motor | Engine team
| Supervisor | Sebbe
MG | Engine setup | Ganesh | Rodrigo
SF | Safety | Someone

## ElectronicPreProcedures
The checking have to be done sequentially to ensure the systems works in the correct way and all steps are correctly followed.
|  |  | Select/Deselect All |  | FALSE
ID | T- | Action | Pre Procedures
|  |  |  | Checkbox | Checkbox links
|  | Phase | General
1 |  | EL1 | Mains power available at test location |  | FALSE
2 |  | EL1 | Measure PSU input for shorts |  | FALSE
3 |  | EL1 | Measure PSU output for shorts |  | FALSE
4 |  | GS | Check that umbilical is connected to controlbox |  | FALSE
5 |  | EL1 | Check that the umbilical is connected at the test bench |  | FALSE
6 |  | EL1 | Plug in the power supply to mains power. |  | FALSE
7 |  | EL1 | Plug in the Rock 4C+ power brick to mains power. |  | FALSE
|  | EL1 | Confirm that there is no smoke. |  | FALSE
|  | Phase | Measure voltages on the power board
|  | EL1 | Verify multimeter function with a 9V battery |  | FALSE
|  | EL1 | Measure 24V voltage output of the PSU |  | FALSE
|  | EL1 | Not applicable in version V1 - Expected Rock 4C+ voltage is 5.1V |  | FALSE
|  | EL1 | Not applicable in version V1 - Expected Servo voltage is 7.8V |  | FALSE
|  | EL1 | Expected Arduino voltage is 7.8V |  | FALSE
|  | EL1 | Measure Arduinos internal 5V voltage |  | FALSE
Electronics Comunications
|  | Phase | Ensure the following:
|  | EL1 | Rock 4C+ power on |  | FALSE
|  | EL1 | USB connection between Rock 4C+ and Arduino (Using a no power USB cable) |  | FALSE
|  | EL1 | Ethernet cable connection between Rock 4C+ and laptop |  | FALSE
|  | Phase | Setting up the laptop terminal
|  | CM | Start the Tilix terminal application on the laptop (windows button and then search) |  | FALSE
|  | CM | Use ctrl+alt+a to open a new terminal window inside Tilix (3 should be enough) |  | FALSE
|  | CM | Left click or use alt+[arrow key] to navigate between terminal windows |  | FALSE
|  | Phase | Data reading and backup
|  | CM | Use “ ping rock-4c-plus.local ” to ensure ethernet connection and confirm zero packet loss |  | FALSE
|  | CM | Use " ssh rock@rock-4c-plus.local ” to remote connect to Rock 4C+ |  | FALSE
|  | CM | In the ssh terminal (opened in previous step) use " sudo python3 scripts/serial_reader.py ” to start reading serial data and save it to the Rock 4C+ |  | FALSE
|  | CM | Use “ ssh rock@rock-4c-plus.local “tail -f scripts/data.csv” ¦ tee data.csv ” to get a live reading of the sensor data and write it locally to the laptop |  | FALSE
|  | CM | Use “python3 live_grapher_opt_V2.py” to start live graphing the sensor data |  | FALSE
|  | Phase | Coordinate with GSE (Control Box Operator)
|  | GS | Verify that the main power relay can be activated from the control box. |  | FALSE
|  | GS | Confirm that E-Stop button not pressed. |  | FALSE
|  | EL 1 | Measure the voltage between PSU_24V and 24V. |  | FALSE
|  | EL1 | Confirm 0 voltage |  | FALSE
|  | GS | Confirm that E-Stop button pressed. |  | FALSE
|  | EL1 | Measure the voltage between PSU_24V and 24V. |  | FALSE
|  | EL 1 | Confirm 24 V |  | FALSE
|  | Phase | Verify that the two primary ignition relays can be activated from the control box.
|  | GS | GS confirms ignition button and key are not pressed. |  | FALSE
|  | EL1 | EL 1 measures continuity between IGN_GND and PGND |  | FALSE
|  | EL1 | EL 1 confirms no continuity. |  | FALSE
|  | El1 | EL 1 measures voltage between 24V and IGNISENSE |  | FALSE
|  | EL1 | EL 1 confirms 24V voltage. |  | FALSE
|  | GS | GS confirms ignition button and key are pressed. |  | FALSE
|  | EL1 | EL 1 measures continuity between IGN_GND and PGND |  | FALSE
|  | EL1 | EL 1 confirms continuity. |  | FALSE
|  | EL1 | EL 1 measures voltage between 24V and IGNISENSE |  | FALSE
|  | EL1 | EL 1 confirms <50mV voltage. |  | FALSE
|  | Phase | Verify that the heating blanket relay can be activated from the control box.
|  | GS | GS confirms heating blanket button is not pressed. |  | FALSE
|  | EL1 | EL 1 measures voltage between 24V and HEATING |  | FALSE
|  | EL1 | EL 1 confirms 24V voltage. |  | FALSE
|  | GS | GS confirms heating blanket button is pressed. |  | FALSE
|  | EL1 | EL 1 measures voltage between 24V and HEATING |  | FALSE
|  | EL1 | EL 1 confirms <50mV voltage. |  | FALSE
Verify the oxidizer valve can be activated from the control box.
|  | El1 | EL 1 confirm readiness to listen for the valve actuation. |  | FALSE
|  | GS | GS press manual valve button. |  | FALSE
|  | EL1 | EL 1 confirm the valve opens. |  | FALSE
|  | GS | GS release the manual valve button. |  | FALSE
|  | EL1 | EL 1 confirm the valve closes. |  | FALSE
Sensor
Signature EL:
Signature MC:
Full sequence test
Primary Igniter relays when GS presses button.
Secondary igniter relay after ~1 second.
Oxidizer valve opens after ~2 seconds.
Secondary igniter relay after ~3 seconds.
Oxidizer valve after N seconds (depends on the wanted burn length, 6-10 seconds).
Primary Igniter relays after GS releases button.